LeapMoney

Sprint 0 — Execution-Ready Backlog

Version 1.0  ·  June 2026  ·  Engineering Team

8 Epics  ·  26 Stories  ·  134 Story Points  ·  2 Weeks

| Epic | Title | Stories | Points | Primary Owner |
| --- | --- | --- | --- | --- |
| 1 | GitHub Setup | 3 | 10 | E1 — Tech Lead |
| 2 | Turborepo & Monorepo Setup | 3 | 16 | E1 — Tech Lead |
| 3 | Next.js App Setup | 3 | 14 | E1 + E2 |
| 4 | Supabase Setup | 4 | 29 | E1 — Tech Lead |
| 5 | CI/CD Setup | 3 | 16 | E1 — Tech Lead |
| 6 | Design System Setup | 3 | 18 | E2 — Full-Stack |
| 7 | Authentication | 4 | 18 | E1 + E2 |
| 8 | RBAC | 3 | 13 | E1 + E2 |
|  | TOTAL | 26 | 134 |  |

# Sprint 0 Overview

| Field | Value |
| --- | --- |
| Sprint Number | Sprint 0 — Foundation Sprint |
| Duration | 2 Weeks (14 calendar days) |
| Sprint Goal | Establish the complete technical foundation — monorepo, CI/CD, database schema, auth, RBAC, and design system — so that Sprint 1 feature development begins on a production-grade base with zero infrastructure debt. |
| Team | E1 (Tech Lead / Full-Stack), E2 (Full-Stack Engineer). E3 (Contract) joins Sprint 3. |
| E1 Point Load | ~91 story points (infrastructure-heavy; intentional for Sprint 0) |
| E2 Point Load | ~43 story points (design system, Next.js scaffold, auth flows) |
| Daily Standup | Async text standup in team channel by 10:00 AM IST daily (format per Phase 12 Section 9.1) |
| Sprint Review | End of Week 2 — demo working app scaffold with auth flow to Founder |
| Sprint Retrospective | End of Week 2 — 45 minutes; update CLAUDE.md and coding standards if needed |
| Definition of Done | Per Phase 12 Section 9.3 (15-item DoD checklist); all stories must pass DoD before Sprint 1 |
| Story Point Scale | 1 pt ≈ 2 hours of focused engineering work; 8 pts ≈ 1 full day; 13 pts = complex (break down if possible) |
| Velocity Target | This is Sprint 0; velocity data does not exist yet. Use this sprint to calibrate true velocity for Sprint 1 planning. |

Sprint 0 Capacity Note E1 carries ~91 points because all infrastructure work falls on the Tech Lead. This is by design — E2 cannot scaffold apps or write migrations until E1 has the monorepo, Supabase, and CI running. E1 stories in Epics 1–5 run sequentially in Week 1; E2 stories in Epics 6–7 can begin in parallel as soon as the monorepo (S0-04) is done. Week 2 is joint delivery of auth, RBAC, and design system.

## Sprint 0 Parallel Execution Map

| Day | E1 Focus | E2 Focus | Sync Point |
| --- | --- | --- | --- |
| Day 1 | S0-01: GitHub Setup | Read codebase conventions from Phase 12; set up local environment | End of Day 1: E1 confirms monorepo is ready for E2 to clone |
| Day 2 | S0-02: Branch protection S0-03: PR templates | S0-07 begins: scaffold apps/web and apps/borrower | — |
| Day 3 | S0-04: Turborepo init | S0-07: scaffold apps/dsa, apps/lender, apps/admin, apps/referral | End of Day 3: E1 merges S0-04; E2 rebases app scaffolds on top |
| Day 4 | S0-05: packages/config S0-08: Env var management | S0-08: Env var setup in each app; S0-17 begins (packages/ui) | — |
| Day 5 | S0-06: Remote caching S0-09: next.config.ts all apps | S0-17: shadcn/ui base config | End of Week 1: monorepo + config complete; schema work begins |
| Day 6 | S0-10: Provision Supabase S0-11: Schema migrations start | S0-18: LeapMoney design tokens | — |
| Day 7 | S0-11: Schema migrations continue | S0-18: Design tokens complete S0-19: Core components start | Daily sync: review token implementation |
| Day 8 | S0-11: Schema migrations complete S0-12: RLS policies start | S0-19: Core components continue | — |
| Day 9 | S0-12: RLS policies complete S0-13: Storage buckets | S0-19: Core components complete S0-21: Borrower OTP start | — |
| Day 10 | S0-14: CI Pipeline | S0-21: Borrower OTP complete S0-22: Staff auth start | End of Day 10: CI must be green to unblock S0-15 |
| Day 11 | S0-15: Vercel deployment S0-16: Security scanning | S0-22: Staff auth complete S0-20: Supabase auth config | — |
| Day 12 | S0-20: Supabase auth config S0-23: Auth middleware | S0-26: Role-based nav shell | Sprint 0 feature freeze — all PRs must be open |
| Day 13 | S0-24: Roles in Supabase S0-25: RBAC guards start | S0-25: RBAC guards (joint) | All PRs merged to develop |
| Day 14 | Sprint review prep; code review any remaining PRs | Sprint review prep; smoke test all 6 apps on staging | Sprint Review with Founder; Retrospective |

# Story Index — All 26 Stories

| Story ID | Title | Epic | Owner | Points | Priority |
| --- | --- | --- | --- | --- | --- |
| S0-01 | Configure GitHub Organisation & Repository | 1 — GitHub | E1 | 5 | Must Have |
| S0-02 | Branch Protection & Repository Settings | 1 — GitHub | E1 | 3 | Must Have |
| S0-03 | PR & Issue Templates | 1 — GitHub | E1 | 2 | Must Have |
| S0-04 | Initialise Turborepo Monorepo with pnpm | 2 — Turborepo | E1 | 8 | Must Have |
| S0-05 | Configure Shared packages/config | 2 — Turborepo | E1 | 5 | Must Have |
| S0-06 | Configure Turborepo Remote Caching | 2 — Turborepo | E1 | 3 | Should Have |
| S0-07 | Scaffold All 6 Next.js Apps | 3 — Next.js | E1+E2 | 8 | Must Have |
| S0-08 | Environment Variable Management | 3 — Next.js | E1 | 3 | Must Have |
| S0-09 | Next.js App-Level Configuration | 3 — Next.js | E2 | 3 | Must Have |
| S0-10 | Provision Supabase Projects (Staging + Prod) | 4 — Supabase | E1 | 3 | Must Have |
| S0-11 | Initial Database Schema Migrations | 4 — Supabase | E1 | 13 | Must Have |
| S0-12 | Row-Level Security Policies | 4 — Supabase | E1 | 8 | Must Have |
| S0-13 | Storage Buckets & Edge Function Scaffold | 4 — Supabase | E1 | 5 | Must Have |
| S0-14 | GitHub Actions CI Pipeline | 5 — CI/CD | E1 | 8 | Must Have |
| S0-15 | Vercel Deployment Configuration | 5 — CI/CD | E1 | 5 | Must Have |
| S0-16 | Security Scanning (Gitleaks + CodeQL) | 5 — CI/CD | E1 | 3 | Must Have |
| S0-17 | Configure packages/ui with shadcn/ui | 6 — Design System | E2 | 5 | Must Have |
| S0-18 | Implement LeapMoney Design Tokens | 6 — Design System | E2 | 5 | Must Have |
| S0-19 | Core Component Library Scaffold | 6 — Design System | E2 | 8 | Must Have |
| S0-20 | Supabase Auth Configuration | 7 — Auth | E1 | 3 | Must Have |
| S0-21 | Borrower OTP Login Flow | 7 — Auth | E2 | 8 | Must Have |
| S0-22 | Staff Email / Password Authentication | 7 — Auth | E2 | 5 | Must Have |
| S0-23 | Auth Middleware & Session Management | 7 — Auth | E1 | 2 | Must Have |
| S0-24 | Roles & Permissions in Supabase | 8 — RBAC | E1 | 5 | Must Have |
| S0-25 | RBAC Middleware Guards & Route Protection | 8 — RBAC | E1+E2 | 5 | Must Have |
| S0-26 | Role-Based Navigation Shell | 8 — RBAC | E2 | 3 | Must Have |

EPIC 1 · GitHub Setup 3 Stories · 10 Story Points

Establish the GitHub organisation, primary repository, access controls, branch protections, and PR/issue templates. This is the first story of Sprint 0 — nothing else can start until the repo exists. Estimated completion: Day 1–2.

S0-01 · Configure GitHub Organisation & Repository ●●●●●○○○ 5 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a Tech Lead, I want to set up the GitHub organisation and primary repository so that the team has a secure, organised home for all source code with correct naming, gitignore, and onboarding documentation from Day 1.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | `leapmoney-platform` GitHub organisation created under the founder's GitHub account; set to private by default for all repos. |
| 2 | Primary repository `leapmoney-platform/platform` created as private. |
| 3 | All team members added with correct permission levels: E1 = Admin, E2 = Write, QA = Write (test branches only), PM = Read. |
| 4 | `.gitignore` in root covers: Node (`node_modules/`), Next.js (`.next/`, `out/`), environment files (`.env*` excluding `.env.example`), OS files (`.DS_Store`, `Thumbs.db`), Turborepo (`.turbo/`), IDE (`.idea/`, `.vscode/` except settings.json). |
| 5 | Root `README.md` exists with: (a) project overview, (b) local dev setup instructions (clone → pnpm install → supabase start → pnpm dev), (c) team roster and Slack channel link, (d) link to Phase 12 Development Execution Blueprint. |
| 6 | `.nvmrc` file at root contains: `20` (Node 20 LTS). |
| 7 | Root `package.json` contains `"engines": { "node": ">=20.0.0", "pnpm": ">=9.0.0" }` to enforce version requirements. |
| 8 | `develop` branch created from `main` as the integration branch (both exist and are empty at this point). |
| 9 | GitHub organisation Plan set to Team ($4/user/month) — required for branch protection rules and CI minute quota. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Create `leapmoney-platform` GitHub organisation; configure org settings (private repos, no forking) | E1 | 0.5h | — |
| 2 | Create private repo `platform`; initialise with README.md and default .gitignore (Node template) | E1 | 0.5h | Org created |
| 3 | Invite all team members (E2, QA, PM) with correct permission levels | E1 | 0.5h | Repo created |
| 4 | Replace generated .gitignore with comprehensive version covering Node, Next.js, .env, OS, Turborepo, IDE | E1 | 0.5h | Repo created |
| 5 | Write root README.md: project overview + local dev setup steps + team roster + blueprint link | E1 | 1.5h | Repo created |
| 6 | Add `.nvmrc` (Node 20) and update root package.json with engines field | E1 | 0.25h | Repo created |
| 7 | Create `develop` branch from `main`; push initial commit | E1 | 0.25h | README committed |
| 8 | Upgrade org to Team plan; verify billing is under founder's account | E1 | 0.25h | Org created |

S0-02 · Branch Protection & Repository Settings ●●●○○○○○ 3 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a Tech Lead, I want to configure branch protection rules and repository settings so that no code reaches `develop` or `main` without a passing PR review and green CI, eliminating the risk of broken code on integration branches.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | `main` branch protection: (a) require PR before merge, (b) require 1 approving review, (c) require status checks to pass (all CI jobs), (d) no direct push for anyone including admins, (e) no force push, (f) no branch deletion, (g) require linear history. |
| 2 | `develop` branch protection: (a) require PR before merge, (b) require 1 approving review, (c) require lint + type-check + unit-test CI jobs to pass, (d) no force push, (e) no branch deletion. |
| 3 | Auto-delete head branches enabled — feature branches are automatically deleted after PR merge. |
| 4 | Default merge strategy set to Squash and merge. |
| 5 | Dependabot alerts enabled via `.github/dependabot.yml`: weekly security alerts for `npm` packages; auto-PR for patch-level updates. |
| 6 | GitHub Actions permissions: allow read access to repository contents; allow write access to pull requests (for posting CI status comments). |
| 7 | Verified: attempt to push directly to `main` from E1 account returns an error (branch protection working). |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Configure `main` branch protection via GitHub Settings → Branches → Branch protection rules | E1 | 0.5h | S0-01 |
| 2 | Configure `develop` branch protection with same settings minus linear history requirement | E1 | 0.25h | S0-01 |
| 3 | Enable auto-delete head branches in GitHub Settings → General | E1 | 0.1h | S0-01 |
| 4 | Set default merge strategy to Squash and merge in GitHub Settings → General | E1 | 0.1h | S0-01 |
| 5 | Create `.github/dependabot.yml` with npm ecosystem, weekly schedule, open PRs for patch updates | E1 | 0.5h | S0-01 |
| 6 | Configure GitHub Actions permissions (Settings → Actions → General) | E1 | 0.1h | S0-01 |
| 7 | Test branch protection: attempt direct push to main; verify rejection | E1 | 0.25h | All above |

S0-03 · PR & Issue Templates ●●○○○○○○ 2 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a any engineer, I want to have PR and issue templates auto-populated on every new PR or issue so that I never accidentally submit an incomplete PR or missing bug report, and the team maintains consistent communication quality throughout the sprint.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | `.github/pull_request_template.md` created with: (a) story link field, (b) change description, (c) all 15 DoD checklist items from Phase 12 Appendix B as checkboxes, (d) "How to test" section, (e) screenshots field (optional). |
| 2 | `.github/ISSUE_TEMPLATE/bug_report.md` created with: priority selector (P0/P1/P2/P3), description, steps to reproduce, expected vs actual behaviour, environment (browser, OS, app), Sentry link field. |
| 3 | `.github/ISSUE_TEMPLATE/feature_request.md` created with: problem statement, proposed solution, acceptance criteria, story points estimate, priority. |
| 4 | Templates auto-populate on new PR/issue creation — verified by opening a test PR and test issue in the repository. |
| 5 | PR template includes: `Resolves: [story ID]` field at the top so every PR is traceable to a backlog story. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Create `.github/` directory with `ISSUE_TEMPLATE/` subdirectory | E1 | 0.1h | S0-01 |
| 2 | Write `pull_request_template.md` with all DoD checkboxes and required fields | E1 | 0.5h | S0-01 |
| 3 | Write `bug_report.md` issue template | E1 | 0.5h | S0-01 |
| 4 | Write `feature_request.md` issue template | E1 | 0.25h | S0-01 |
| 5 | Open test PR and test issue to verify templates load correctly; close both without merging | E1 | 0.25h | All templates committed |

EPIC 2 · Turborepo & Monorepo Setup 3 Stories · 16 Story Points

Initialise the Turborepo monorepo with pnpm workspaces, configure shared base packages (ESLint, TypeScript, Tailwind), and enable remote caching. This is the structural backbone of the entire platform — every subsequent story depends on it.

S0-04 · Initialise Turborepo Monorepo with pnpm Workspaces ●●●●●●●● 8 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a Tech Lead, I want to initialise a Turborepo monorepo with pnpm workspaces containing all 6 apps and 5 packages so that every engineer works from a single repository with shared tooling, consistent build pipelines, and parallel task execution from day one.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | `pnpm-workspace.yaml` at root defines workspaces: `apps/*` and `packages/*`. |
| 2 | Root `package.json` has `"private": true`, correct pnpm version pinned (`"packageManager": "pnpm@9.x.x"`), and scripts: `dev`, `build`, `lint`, `type-check`, `test`. |
| 3 | `turbo.json` defines full pipeline: `build` (dependsOn `^build`, outputs `.next/**`, `dist/**`), `dev` (no cache, persistent), `lint` (no cache), `type-check` (dependsOn `^build`), `test` (dependsOn `^build`, outputs `coverage/**`), `test:e2e` (no cache). |
| 4 | `apps/` directory contains 6 subdirectories: `web`, `borrower`, `dsa`, `lender`, `admin`, `referral` — each with a minimal `package.json` using name format `@leapmoney/<app-name>`. |
| 5 | `packages/` directory contains 5 subdirectories: `ui`, `supabase`, `types`, `analytics`, `config` — each with a minimal `package.json` using name `@leapmoney/<package-name>`. |
| 6 | `.npmrc` at root contains: `shamefully-hoist=false` and `strict-peer-dependencies=false`. |
| 7 | `pnpm install` runs from root with no errors and generates `pnpm-lock.yaml`. |
| 8 | `pnpm turbo build` resolves the dependency graph without errors (tasks no-op since no build scripts exist yet — this is expected). |
| 9 | Tech Lead can demonstrate: running `pnpm --filter @leapmoney/borrower dev` targets only the borrower app. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Install pnpm globally on all dev machines; verify version | E1 | 0.25h | S0-01 |
| 2 | Initialise root `package.json` via `pnpm init`; set name, private, packageManager fields | E1 | 0.5h | S0-01 |
| 3 | Create `pnpm-workspace.yaml` defining `apps/*` and `packages/*` workspaces | E1 | 0.25h | root package.json |
| 4 | Install Turborepo: `pnpm add -D turbo -w` | E1 | 0.25h | workspace yaml |
| 5 | Write `turbo.json` with complete pipeline definition for all 6 task types | E1 | 1.5h | Turborepo installed |
| 6 | Create `apps/` directory with 6 subdirectories; write minimal `package.json` in each (name + version) | E1 | 1h | root structure |
| 7 | Create `packages/` directory with 5 subdirectories; write minimal `package.json` in each | E1 | 0.75h | root structure |
| 8 | Create `.npmrc` with shamefully-hoist and strict-peer-dependencies settings | E1 | 0.1h | — |
| 9 | Run `pnpm install` from root; fix any workspace resolution errors; commit lock file | E1 | 0.5h | All package.json files |
| 10 | Run `pnpm turbo build` and verify pipeline graph resolves; commit | E1 | 0.5h | pnpm install clean |

S0-05 · Configure Shared packages/config ●●●●●○○○ 5 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a any engineer, I want to have shared ESLint, TypeScript, and Tailwind base configurations in `packages/config` so that all 6 apps share identical tooling settings without duplicating config files, and any change to a standard is applied everywhere in one commit.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | `packages/config/package.json` exports 3 configuration modules via `"exports"` field: `./eslint`, `./typescript`, `./tailwind`. |
| 2 | `packages/config/eslint/index.js` defines base ESLint rules: TypeScript strict rules (`@typescript-eslint/recommended-type-checked`), import ordering (`eslint-plugin-import`), React rules (`eslint-plugin-react`, `eslint-plugin-react-hooks`), Next.js rules (`eslint-config-next`), `no-console` as error, `@typescript-eslint/no-explicit-any` as error. |
| 3 | `packages/config/tsconfig/base.json` contains all TypeScript settings from Phase 12 Section 5.1: `strict: true`, `noUncheckedIndexedAccess: true`, `exactOptionalPropertyTypes: true`, `noImplicitReturns: true`, `allowJs: false`, `target: "ES2022"`, `moduleResolution: "bundler"`. |
| 4 | `packages/config/tailwind/base.ts` extends Tailwind defaults with LeapMoney colour tokens: `leap-teal` (#0F766E), `leap-navy` (#1E3A5F), `leap-green` (#059669), `leap-amber` (#F59E0B) — matching Phase 6 design system. |
| 5 | Each of the 6 apps has an `eslint.config.js` that extends `@leapmoney/config/eslint`. |
| 6 | Each app has a `tsconfig.json` extending `@leapmoney/config/typescript`. |
| 7 | Each app has a `tailwind.config.ts` extending `@leapmoney/config/tailwind`. |
| 8 | `pnpm turbo lint` runs across all apps with 0 errors and 0 warnings on the empty scaffold. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Set up `packages/config/package.json` with exports field for eslint, typescript, tailwind modules | E1 | 0.5h | S0-04 |
| 2 | Install ESLint and all plugins as devDependencies in packages/config | E1 | 0.5h | config package.json |
| 3 | Write `eslint/index.js` with full rule set including no-console and no-any as errors | E1 | 1.5h | plugins installed |
| 4 | Write `tsconfig/base.json` with all strict settings from Phase 12 Section 5.1 | E1 | 0.5h | — |
| 5 | Write `tailwind/base.ts` with LeapMoney colour tokens from Phase 6 design system | E1 | 0.5h | — |
| 6 | Add `eslint.config.js`, `tsconfig.json`, `tailwind.config.ts` to each of 6 apps extending config package | E1 | 1h | config package complete |
| 7 | Run `pnpm turbo lint` from root; fix any import or resolution errors | E1 | 0.5h | All app configs |

S0-06 · Configure Turborepo Remote Caching ●●●○○○○○ 3 pts · Owner: E1 — Tech Lead · Priority: Should Have

As a Tech Lead, I want to configure Turborepo remote caching via Vercel so that CI build times are minimised — subsequent CI runs on unchanged code take seconds instead of minutes, and every engineer benefits from cache hits created by other engineers or CI.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | Vercel Remote Cache linked to the Turborepo workspace using the Vercel account connected to the project. |
| 2 | `TURBO_TOKEN` (Vercel access token) and `TURBO_TEAM` (Vercel team slug) added to GitHub Actions secrets. |
| 3 | `TURBO_TOKEN` and `TURBO_TEAM` documented in `.env.example` with clear instructions (do not commit real values). |
| 4 | Local dev setup documented in README under "Remote Cache Setup": `npx turbo login` → `npx turbo link`. |
| 5 | Cache hit verified: running `pnpm turbo build` twice from a clean state — second run shows ">>> FULL TURBO" in output (all tasks restored from cache). |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Create Vercel account (or use existing); install Vercel CLI: `pnpm add -g vercel` | E1 | 0.5h | S0-04 |
| 2 | Run `npx turbo login` and `npx turbo link` to connect remote cache | E1 | 0.5h | Vercel CLI |
| 3 | Add `TURBO_TOKEN` and `TURBO_TEAM` to GitHub Actions secrets | E1 | 0.25h | Vercel connected |
| 4 | Update `.env.example` with TURBO_TOKEN and TURBO_TEAM placeholders and instructions | E1 | 0.25h | — |
| 5 | Update README "Remote Cache Setup" section with turbo login/link steps | E1 | 0.5h | — |
| 6 | Verify cache hit: run build twice; confirm FULL TURBO on second run | E1 | 0.25h | Cache linked |

EPIC 3 · Next.js App Setup 3 Stories · 14 Story Points

Scaffold all 6 Next.js 14 App Router applications with the standard folder structure, environment variable management, and app-level configuration (security headers, Sentry, next.config.ts). Engineers must be able to clone the repo and run any app in under 5 minutes.

S0-07 · Scaffold All 6 Next.js Apps ●●●●●●●● 8 pts · Owner: E1 + E2 · Priority: Must Have

As a any engineer, I want to have all 6 Next.js apps scaffolded with the standard folder structure from Phase 12 Section 4.1 so that feature development in Sprint 1 can begin immediately — no engineer spends Sprint 1 time on folder structure or app setup.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | Each of 6 apps (`web`, `borrower`, `dsa`, `lender`, `admin`, `referral`) is initialised with Next.js 14 App Router + TypeScript strict mode. |
| 2 | Every app follows the exact folder structure from Phase 12 Section 4.1: `src/app/`, `src/components/`, `src/hooks/`, `src/lib/`, `src/types/`, `src/middleware.ts`. |
| 3 | Every app has route groups: `src/app/(auth)/` and `src/app/(dashboard)/` with stub `layout.tsx` in each. |
| 4 | Root-level app files exist in every app: `src/app/layout.tsx` (with font loading and providers), `src/app/error.tsx`, `src/app/not-found.tsx`, `src/app/globals.css` (Tailwind base import). |
| 5 | Supabase client stubs exist: `src/lib/supabase/client.ts` (browser client factory) and `src/lib/supabase/server.ts` (server client factory) — both export placeholder functions that will be wired in S0-20. |
| 6 | `src/middleware.ts` stub exists in every app — exports a `middleware` function and `config.matcher` protecting the `(dashboard)` route group (redirects to /login if no session). |
| 7 | `pnpm turbo type-check` passes for all 6 apps with 0 TypeScript errors. |
| 8 | Every app's stub home page (`src/app/(dashboard)/page.tsx`) renders: app name + "Sprint 0 scaffold — authentication coming in S0-21" — confirming routing works end-to-end. |
| 9 | `pnpm --filter @leapmoney/borrower dev` starts the borrower dev server on port 3001; other apps use ports 3000, 3002, 3003, 3004, 3005. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | E1: Scaffold `apps/web` using Next.js 14 App Router template; apply standard folder structure | E1 | 1h | S0-04 |
| 2 | E1: Scaffold `apps/borrower`; apply standard folder structure + Supabase stubs + middleware stub | E1 | 1h | S0-04 |
| 3 | E2: Scaffold `apps/dsa` with same standard structure (clone from borrower pattern) | E2 | 0.75h | S0-04 |
| 4 | E2: Scaffold `apps/lender` with standard structure | E2 | 0.75h | S0-04 |
| 5 | E2: Scaffold `apps/admin` with standard structure | E2 | 0.75h | S0-04 |
| 6 | E2: Scaffold `apps/referral` with standard structure (minimal — Phase 2 app) | E2 | 0.5h | S0-04 |
| 7 | E1: Configure port assignments in each app's package.json dev script (3000–3005) | E1 | 0.5h | All apps scaffolded |
| 8 | E1: Run `pnpm turbo type-check` across all apps; fix TypeScript errors | E1 | 1h | All scaffolds done |
| 9 | E1: Smoke test: run each app's dev server; confirm stub home page loads | E1 | 0.5h | type-check passes |

S0-08 · Environment Variable Management ●●●○○○○○ 3 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a any engineer, I want to have a consistent, type-safe environment variable system across all apps so that required env vars are validated at build time (build fails if missing), no secret is ever hardcoded, and any new engineer knows exactly what vars to configure in under 5 minutes.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | `.env.example` at repo root documents ALL required environment variables with descriptions and placeholder values. Variables grouped by: Supabase, 360dialog WhatsApp, Razorpay, CIBIL/Experian bureau, Sentry, Turborepo Cache, Analytics. |
| 2 | Every app has a `src/lib/env.ts` that validates all required env vars at startup using Zod (or `@t3-oss/env-nextjs`). Build fails with a descriptive error if a required var is missing. |
| 3 | All client-side variables use `NEXT_PUBLIC_` prefix; all server-side secrets use no prefix and are never exposed to the client bundle. |
| 4 | Each app's `.env.local` (gitignored) is pre-populated with staging Supabase URL and anon key for local dev — documented in README. |
| 5 | `.gitignore` confirmed to exclude: `.env.local`, `.env.production`, `.env.staging`, `.env*.local` (all local env files). |
| 6 | README has "Environment Setup" section: copy `.env.example` → `.env.local`, where to find each value (1Password vault / Supabase dashboard / third-party dashboards). |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Create `.env.example` at root with all required vars, descriptions, and placeholder values | E1 | 1h | S0-10 (to know Supabase URL) |
| 2 | Write `src/lib/env.ts` in each app using Zod to validate required env vars at startup | E1 | 1h | S0-07 |
| 3 | Verify client/server variable naming: audit all `process.env` references for correct prefix usage | E1 | 0.5h | env.ts in all apps |
| 4 | Update `.gitignore` to ensure all local env file patterns are excluded | E1 | 0.1h | — |
| 5 | Write README "Environment Setup" section with step-by-step instructions | E1 | 0.5h | — |
| 6 | Test: intentionally remove a required env var; confirm build fails with descriptive error | E1 | 0.25h | env.ts complete |

S0-09 · Next.js App-Level Configuration ●●●○○○○○ 3 pts · Owner: E2 — Full-Stack · Priority: Must Have

As a any engineer, I want to have each Next.js app configured with security headers, strict build rules, and Sentry error tracking so that production-grade settings are in place from Day 1 and do not need to be retrofitted later under time pressure before launch.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | `next.config.ts` in each app configures: (a) `reactStrictMode: true`, (b) `typescript.ignoreBuildErrors: false` (build fails on TypeScript errors), (c) `eslint.ignoreDuringBuilds: false` (build fails on ESLint errors), (d) image `remotePatterns` allowing Supabase Storage URL. |
| 2 | Security headers added to `next.config.ts` via `headers()` function: `X-Frame-Options: DENY`, `X-Content-Type-Options: nosniff`, `Referrer-Policy: strict-origin-when-cross-origin`, `Permissions-Policy: camera=(), microphone=(), geolocation=()`. |
| 3 | Content Security Policy header defined (strict; allows Supabase, Google Analytics, Sentry domains). |
| 4 | Sentry initialised in each app via `@sentry/nextjs`: `sentry.client.config.ts`, `sentry.server.config.ts`, `sentry.edge.config.ts` exist and are wired into the Next.js config via `withSentryConfig()`. |
| 5 | Sentry DSN read from `process.env.SENTRY_DSN` — not hardcoded anywhere. |
| 6 | `pnpm turbo build` passes for all 6 apps with 0 errors after configuration is applied. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Write `next.config.ts` for each app with reactStrictMode, typescript, eslint, and image settings | E2 | 1h | S0-07 |
| 2 | Add security headers (X-Frame-Options, X-Content-Type-Options, Referrer-Policy, Permissions-Policy) to each app's next.config.ts | E2 | 0.75h | next.config.ts created |
| 3 | Define CSP header allowing Supabase, GA4, Sentry, and self origins | E2 | 0.75h | security headers done |
| 4 | Install `@sentry/nextjs` in each app; run Sentry wizard or manually create sentry config files | E2 | 1.5h | S0-07 |
| 5 | Add `SENTRY_DSN` to `.env.example` and `env.ts` validation; confirm Sentry reads from env | E2 | 0.5h | Sentry installed |
| 6 | Run `pnpm turbo build` across all 6 apps; fix any config errors | E2 | 0.5h | All configs applied |

EPIC 4 · Supabase Setup 4 Stories · 29 Story Points

Provision Supabase projects, create the complete database schema from Phase 3, implement all Row-Level Security policies, and configure Storage buckets. This is the largest epic in Sprint 0 (29 points) and the critical path for all feature work in Sprint 1 and beyond.

Critical Path Warning S0-11 (Database Migrations) is the single most critical story in Sprint 0. If this is delayed, every Sprint 1 story that touches data is blocked. E1 must begin S0-11 no later than Day 6. S0-12 (RLS) depends on S0-11. S0-20 (Auth config) can be done in parallel with S0-11 — Supabase Auth does not depend on custom schema.

S0-10 · Provision Supabase Projects (Staging + Production) ●●●○○○○○ 3 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a Tech Lead, I want to provision two isolated Supabase projects for staging and production environments so that the team has separate, isolated databases for development/testing and production from Day 1, and we comply with RBI data localisation requirements by hosting in the Mumbai region.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | Two Supabase projects created in the Supabase dashboard: `leapmoney-staging` and `leapmoney-production`. |
| 2 | Both projects use the `ap-south-1` (Mumbai / Asia Pacific South) region — required for RBI data localisation compliance. |
| 3 | Both project URLs and anon keys documented in 1Password under "LeapMoney — Infrastructure Secrets". |
| 4 | Service role keys stored in 1Password and in GitHub Actions secrets (never in `.env.example` or source code). |
| 5 | Supabase CLI installed in monorepo: `pnpm add -D supabase -w`; CLI version confirmed as 1.x or later. |
| 6 | `supabase/config.toml` configured for local dev: correct project ref for staging, local ports defined (API: 54321, Studio: 54323, DB: 54322). |
| 7 | `supabase start` runs successfully in local environment — Postgres + Auth + Storage + Studio all start without errors. |
| 8 | Staging Supabase project linked to the repository via Supabase GitHub integration (optional but recommended for migration auto-deployment). |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Create `leapmoney-staging` Supabase project; select ap-south-1 region; note URL and anon key | E1 | 0.5h | — |
| 2 | Create `leapmoney-production` Supabase project; select ap-south-1 region; note URL and anon key | E1 | 0.25h | — |
| 3 | Store all Supabase credentials (URLs, anon keys, service role keys) in 1Password vault | E1 | 0.5h | Both projects created |
| 4 | Add staging service role key to GitHub Actions secrets as `SUPABASE_SERVICE_ROLE_KEY` | E1 | 0.25h | 1Password done |
| 5 | Install Supabase CLI in monorepo: `pnpm add -D supabase -w` | E1 | 0.25h | S0-04 |
| 6 | Write `supabase/config.toml` with staging project ref and local port configuration | E1 | 0.5h | CLI installed |
| 7 | Run `supabase start` locally; verify all services start; confirm Studio accessible at localhost:54323 | E1 | 0.5h | config.toml done |

S0-11 · Initial Database Schema Migrations ●●●●●●●● 13 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a Tech Lead, I want to create the complete initial database schema as Supabase migration files covering all domain entities from Phase 3 so that every Sprint 1 story can immediately work with real typed data structures — no Sprint 1 time is spent on schema design or table creation.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | Migration `001_initial_schema.sql`: `users` table (id, email, phone, role, is_verified, created_at, updated_at); `profiles` table (user_id FK, full_name, pan_number_hash, date_of_birth, address_json); `consent_log` table (user_id, consent_type, consented_at, ip_address, user_agent). |
| 2 | Migration `002_audit_log.sql`: `audit_log` table — INSERT-only, immutable record of all state changes (id, table_name, record_id, action, changed_by, changed_at, old_values_json, new_values_json). No UPDATE or DELETE ever runs on this table. |
| 3 | Migration `003_lead_application.sql`: `leads` table (id, borrower_id FK, dsa_id FK, loan_type, loan_amount_paise, purpose, status, source, utm_json, created_at); `applications` table (id, lead_id FK, status, submitted_at, lender_id FK); `application_timeline` table (application_id FK, status, changed_at, changed_by). |
| 4 | Migration `004_financial.sql`: `loan_offers` table (application_id FK, lender_id FK, interest_rate_bps, loan_amount_paise, tenure_months, processing_fee_paise, status); `disbursements` table; `commission_ledger` table (dsa_id, application_id, amount_paise, status, paid_at). |
| 5 | Migration `005_dsa.sql`: `dsa_profiles` table (user_id FK, dsa_code, bank_account_json, kyc_status, is_active); `dsa_performance` table (dsa_id, month, leads_count, conversions_count, revenue_paise). |
| 6 | Migration `006_lender.sql`: `lender_profiles` table (user_id FK, lender_name, api_endpoint, is_active); `lender_products` table (lender_id FK, loan_type, min_amount_paise, max_amount_paise, min_cibil, interest_rate_bps). |
| 7 | Migration `007_documents.sql`: `documents` table (id, owner_id FK, application_id FK nullable, document_type, storage_path, file_name, mime_type, is_verified, created_at). |
| 8 | Migration `008_leapscore.sql`: `leapscore_results` table (id, user_id FK, score, band, components_json, computed_at, expires_at); `bureau_pulls` table (user_id, bureau, pulled_at, expires_at, report_ref). |
| 9 | Migration `009_notifications.sql`: `notification_log` table (id, user_id FK, channel, template_id, status, sent_at, message_json); `whatsapp_message_log` table (phone, message_id, template_name, status, sent_at). |
| 10 | Migration `010_triggers.sql`: `updated_at` trigger function `leapmoney_set_updated_at()` applied to all tables with `updated_at` column. |
| 11 | All migrations: run cleanly via `supabase db reset` (wipes local DB and replays all migrations from scratch) with 0 errors. |
| 12 | Generated TypeScript types (`supabase gen types typescript --project-id <staging>`) committed to `packages/supabase/src/types.ts`. |
| 13 | All monetary values stored as integer (paise — 1 INR = 100 paise); floating-point type is never used for money columns. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Write migration 001: users, profiles, consent_log tables with all constraints and indexes | E1 | 2h | S0-10 |
| 2 | Write migration 002: audit_log table with INSERT-only comment; document that no UPDATE/DELETE is ever applied to this table | E1 | 1h | 001 tested |
| 3 | Write migration 003: leads, applications, application_timeline tables with FK relationships and indexes on status + created_at | E1 | 2h | 001 tested |
| 4 | Write migration 004: loan_offers, disbursements, commission_ledger — all amounts as integer (paise) | E1 | 1.5h | 003 tested |
| 5 | Write migrations 005–006: dsa_profiles, dsa_performance, lender_profiles, lender_products | E1 | 1.5h | 003 tested |
| 6 | Write migrations 007–009: documents, leapscore_results, bureau_pulls, notification_log, whatsapp_message_log | E1 | 1.5h | 004 tested |
| 7 | Write migration 010: `leapmoney_set_updated_at()` trigger function; apply to all relevant tables | E1 | 1h | All tables exist |
| 8 | Run `supabase db reset` — confirm all migrations apply cleanly with 0 errors | E1 | 0.5h | All migrations written |
| 9 | Run `supabase gen types typescript`; commit output to `packages/supabase/src/types.ts` | E1 | 0.5h | db reset clean |

S0-12 · Row-Level Security Policies ●●●●●●●● 8 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a Tech Lead, I want to implement RLS policies on all database tables so that multi-tenant data isolation is enforced at the database level — no application bug, no matter how severe, can expose one user's data to another user.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | RLS enabled (`ALTER TABLE x ENABLE ROW LEVEL SECURITY`) on every table in the schema — no exceptions. Confirmed via `SELECT tablename, rowsecurity FROM pg_tables WHERE schemaname = 'public'`. |
| 2 | `users` + `profiles`: SELECT/UPDATE allowed only where `auth.uid() = id` (or `auth.uid() = user_id`). No DELETE. Admin role bypasses via service role key. |
| 3 | `leads`: borrower sees only their own leads (`borrower_id = auth.uid()`); DSA sees only leads where `dsa_id` matches their DSA profile; lenders see no leads table rows; admins (service role) see all. |
| 4 | `applications`: borrower sees their own; DSA sees applications linked to their leads; lender sees applications where `lender_id` matches their lender profile; admins see all. |
| 5 | `dsa_profiles`, `dsa_performance`, `dsa_commissions`: DSA sees only their own rows; no cross-DSA visibility; admins see all. |
| 6 | `lender_profiles`, `lender_products`, `lender_decisions`: lender sees only their own; admins see all. |
| 7 | `documents`: uploader sees their own; documents with `application_id` are visible to the lender on that application; admins see all. |
| 8 | `leapscore_results`, `bureau_pulls`: borrower sees their own; DSA sees results for their leads; lenders see results for their applications; admins see all. |
| 9 | `audit_log`: no user or DSA or lender can SELECT from audit_log; service role only. INSERT is allowed for authenticated users (append-only). |
| 10 | `notification_log`, `whatsapp_message_log`: users see their own notification history; admins see all. |
| 11 | RLS tested using Supabase SQL editor with role-switching: `SET ROLE anon;` and `SET LOCAL "request.jwt.claims" = ...` to simulate each role; cross-tenant data verified to return 0 rows. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Enable RLS on all tables in migration `011_enable_rls.sql`; verify via pg_tables query | E1 | 0.5h | S0-11 |
| 2 | Write RLS policies for users, profiles, consent_log in migration `012_rls_users.sql` | E1 | 1h | RLS enabled |
| 3 | Write RLS policies for leads, applications, application_timeline in `013_rls_leads.sql` | E1 | 1.5h | RLS enabled |
| 4 | Write RLS policies for financial tables (loan_offers, commission_ledger) in `014_rls_financial.sql` | E1 | 1h | RLS enabled |
| 5 | Write RLS policies for dsa and lender tables in `015_rls_dsa_lender.sql` | E1 | 1h | RLS enabled |
| 6 | Write RLS policies for documents, leapscore, bureau_pulls in `016_rls_documents_score.sql` | E1 | 1h | RLS enabled |
| 7 | Write RLS policies for audit_log (INSERT only; no SELECT) and notification tables in `017_rls_audit_notifications.sql` | E1 | 0.5h | RLS enabled |
| 8 | Test all policies using Supabase SQL editor with role-switching; document test results | E1 | 1.5h | All RLS migrations |

S0-13 · Storage Buckets & Edge Function Scaffold ●●●●●○○○ 5 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a Tech Lead, I want to configure Supabase Storage buckets and create Edge Function scaffolds so that document uploads work securely in Sprint 1, and Edge Functions (for WhatsApp dispatch and LeapScore async compute) have a place to live from day one.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | Three Storage buckets created in both staging and production Supabase projects: `documents` (private — borrower KYC docs), `lender-packets` (private — loan application packets for lenders), `avatars` (public — profile photos, optional). |
| 2 | `documents` bucket: max file size 10 MB; allowed MIME types: PDF, JPEG, PNG, HEIC. RLS policy: owner can INSERT and SELECT their own files; lenders can SELECT files for their applications; no DELETE by application users. |
| 3 | `lender-packets` bucket: max file size 20 MB; allowed types: PDF, ZIP. RLS: lender can SELECT their own packets; service role handles INSERT. |
| 4 | Supabase Edge Functions directory exists: `supabase/functions/`. Two stub Edge Functions created: `send-whatsapp/index.ts` (stub — responds with 200 and logs request) and `compute-leapscore-async/index.ts` (stub). |
| 5 | `supabase functions serve send-whatsapp` runs locally without errors (Deno runtime). |
| 6 | Storage bucket URLs documented in `.env.example` as `NEXT_PUBLIC_SUPABASE_STORAGE_URL`. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Create `documents` bucket in staging Supabase dashboard; set max size and allowed MIME types | E1 | 0.5h | S0-10 |
| 2 | Create `lender-packets` and `avatars` buckets in staging; configure settings | E1 | 0.25h | S0-10 |
| 3 | Repeat bucket creation for production Supabase project | E1 | 0.25h | S0-10 |
| 4 | Write Storage RLS migration `018_rls_storage.sql` for documents and lender-packets buckets | E1 | 1h | S0-12 |
| 5 | Create `supabase/functions/send-whatsapp/index.ts` stub with correct Deno import map | E1 | 1h | S0-10 |
| 6 | Create `supabase/functions/compute-leapscore-async/index.ts` stub | E1 | 0.5h | S0-10 |
| 7 | Run `supabase functions serve send-whatsapp` locally; confirm 200 response | E1 | 0.25h | Function stubs created |
| 8 | Add storage URL to `.env.example` and document which bucket each document type uses | E1 | 0.25h | Buckets created |

EPIC 5 · CI/CD Setup 3 Stories · 16 Story Points

Build the GitHub Actions CI pipeline (lint, type-check, unit tests, integration tests), configure Vercel for automatic preview and production deployments, and add security scanning (Gitleaks secret detection + CodeQL static analysis). Once done, every PR gets a preview URL and a full CI run automatically.

S0-14 · GitHub Actions CI Pipeline ●●●●●●●● 8 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a Tech Lead, I want to configure a GitHub Actions CI pipeline that runs on every PR and push to develop so that broken code is caught automatically before it reaches the integration branch — no engineer can merge a PR with failing lint, type errors, or failing tests.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | `.github/workflows/ci.yml` exists and triggers on: push to `develop` and `main`, and on `pull_request` targeting `develop` or `main`. |
| 2 | CI pipeline runs these jobs in order: (1) `lint` — runs `pnpm turbo lint` across all packages and apps, (2) `type-check` — runs `pnpm turbo type-check`, (3) `unit-test` — runs `pnpm turbo test` with coverage output, (4) `integration-test` — runs integration tests against a local Supabase instance (started via `supabase start` in CI). |
| 3 | Jobs run in parallel where dependencies allow: `lint` and `type-check` run in parallel; `unit-test` runs after `type-check` passes; `integration-test` runs after `unit-test` passes. |
| 4 | Turborepo remote cache used in CI: `TURBO_TOKEN` and `TURBO_TEAM` read from GitHub Actions secrets; subsequent CI runs on unchanged code complete in under 60 seconds. |
| 5 | CI uses Node 20 LTS (set via `actions/setup-node@v4` with `node-version: "20"`); pnpm 9.x installed via `pnpm/action-setup@v3`. |
| 6 | CI caches `pnpm store` between runs using `actions/cache@v4` on `pnpm-lock.yaml` hash key. |
| 7 | Branch protection rule on `develop` and `main` requires all 4 CI jobs to pass before merge is permitted. |
| 8 | CI run time on a cold cache (first run): under 8 minutes. With Turborepo cache hit: under 90 seconds. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Write `.github/workflows/ci.yml` skeleton: trigger conditions, job structure, Node/pnpm setup | E1 | 1h | S0-04, S0-05 |
| 2 | Add `lint` job: `pnpm turbo lint`; configure to fail fast on first error | E1 | 0.5h | ci.yml skeleton |
| 3 | Add `type-check` job: `pnpm turbo type-check` | E1 | 0.5h | ci.yml skeleton |
| 4 | Add `unit-test` job: `pnpm turbo test`; upload coverage artifact | E1 | 0.5h | type-check job |
| 5 | Add `integration-test` job: start local Supabase via `supabase start`; run integration tests against it; teardown | E1 | 2h | S0-11 |
| 6 | Add pnpm store caching to CI using actions/cache on pnpm-lock.yaml hash | E1 | 0.5h | ci.yml base |
| 7 | Add Turborepo remote cache env vars (TURBO_TOKEN, TURBO_TEAM) to CI workflow | E1 | 0.25h | S0-06 |
| 8 | Open a test PR; verify all 4 CI jobs run and pass; verify timing | E1 | 0.5h | All jobs configured |

S0-15 · Vercel Deployment Configuration ●●●●●○○○ 5 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a Tech Lead, I want to configure Vercel to automatically deploy preview URLs for every PR and production deployments on merges to main so that every PR gets a live preview URL for immediate testing, and production deployments are automated without manual intervention.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | Vercel project created for each of the 5 MVP apps (`web`, `borrower`, `dsa`, `lender`, `admin`); `referral` deferred to Phase 2. |
| 2 | Each Vercel project linked to the corresponding `apps/<name>` directory in the monorepo (Vercel detects Turborepo automatically). |
| 3 | Vercel environment variables configured for each app: `NEXT_PUBLIC_SUPABASE_URL`, `NEXT_PUBLIC_SUPABASE_ANON_KEY` (staging values in Preview env; production values in Production env). |
| 4 | Automatic deployments: push to `develop` → staging deployment; merge to `main` → production deployment. |
| 5 | Preview deployments: every PR gets a unique preview URL (`<hash>-leapmoney-<app>.vercel.app`) — URL posted automatically to the PR as a comment. |
| 6 | Custom domains configured (or documented as to-do): `leapmoney.net` (web), `app.leapmoney.net` (borrower), `dsa.leapmoney.net` (dsa), `lender.leapmoney.net` (lender), `admin.leapmoney.net` (admin). |
| 7 | `vercel.json` in repo root (if needed) configures: framework preset, build command (`pnpm turbo build --filter=@leapmoney/<app>`), output directory. |
| 8 | Verified: merging a test PR to `develop` triggers a staging deployment; deployment completes successfully. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Create Vercel team account under LeapMoney organisation; add all team members | E1 | 0.5h | S0-04 |
| 2 | Create Vercel project for `apps/web`; link to monorepo; configure build settings | E1 | 0.75h | S0-07 |
| 3 | Create Vercel projects for `apps/borrower`, `apps/dsa`, `apps/lender`, `apps/admin` | E1 | 1.5h | S0-07 |
| 4 | Configure environment variables in each Vercel project (Preview = staging Supabase; Production = production Supabase) | E1 | 1h | Projects created, S0-10 |
| 5 | Add remaining env vars to Vercel (Sentry DSN, 360dialog, Razorpay — staging values for Preview; production for Production) | E1 | 0.5h | Env vars configured |
| 6 | Test: merge a dummy PR to develop; confirm all 5 apps deploy to staging; check deployment logs | E1 | 0.5h | All projects configured |

S0-16 · Security Scanning Pipeline ●●●○○○○○ 3 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a Tech Lead, I want to have automated security scanning on every PR so that secret leaks and common code vulnerabilities are caught automatically before any code reaches the integration branch — protecting client financial data and API credentials.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | `.github/workflows/security.yml` exists and triggers on every PR targeting `develop` or `main`, and on push to both branches. |
| 2 | Gitleaks secret detection: runs `gitleaks/gitleaks-action@v2`; fails the PR if any secret pattern (API key, password, connection string) is detected in the diff. |
| 3 | CodeQL static analysis: runs `github/codeql-action` for JavaScript/TypeScript; analyses for security vulnerabilities (SQL injection patterns, XSS, prototype pollution, path traversal); reports findings as PR annotations. |
| 4 | `.gitleaks.toml` configuration file exists at root to: (a) allowlist known false positives (e.g. test mock values that look like keys), (b) set severity thresholds. |
| 5 | Both Gitleaks and CodeQL jobs are added to the branch protection requirements for `develop` and `main`. |
| 6 | Test verification: intentionally add a fake API key pattern to a test file in a throwaway branch; confirm Gitleaks blocks the PR. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Write `.github/workflows/security.yml` with Gitleaks and CodeQL job definitions | E1 | 1h | S0-01 |
| 2 | Create `.gitleaks.toml` with allowlist for known test fixture values | E1 | 0.5h | Gitleaks job |
| 3 | Add security jobs (gitleaks + codeql) to branch protection requirements for develop and main | E1 | 0.25h | S0-14 jobs passing |
| 4 | Test: commit a fake secret to a throwaway branch; open PR; confirm Gitleaks blocks merge | E1 | 0.5h | Security workflow |
| 5 | Review initial CodeQL findings on the scaffold; fix any real findings; document known false positives | E1 | 0.75h | CodeQL first run |

EPIC 6 · Design System Setup 3 Stories · 18 Story Points

Configure the shared component library (`packages/ui`) with shadcn/ui as the base, implement LeapMoney design tokens from Phase 6, and build the core component scaffold that Sprint 1 feature stories can use immediately. E2 owns this epic entirely.

S0-17 · Configure packages/ui with shadcn/ui ●●●●●○○○ 5 pts · Owner: E2 — Full-Stack · Priority: Must Have

As a Full-Stack Engineer, I want to configure `packages/ui` with shadcn/ui as the component foundation so that all 6 apps share a single source of truth for UI components — no duplicated Button, Input, or Card implementations across apps.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | `packages/ui/package.json` is configured as a proper shared package: name `@leapmoney/ui`, exports `./src/index.ts`, peer dependencies on React 18 and Tailwind 3.x. |
| 2 | shadcn/ui initialised in `packages/ui` via `npx shadcn@latest init` with configuration: TypeScript, Tailwind CSS, CSS variables for theming, `src/components/ui` as components directory. |
| 3 | Base shadcn/ui components installed: `Button`, `Input`, `Label`, `Card`, `Badge`, `Dialog`, `Sheet`, `Table`, `Form`, `Select`, `Checkbox`, `RadioGroup`, `Textarea`, `Separator`, `Skeleton`, `Toast`, `Sonner` (notifications). |
| 4 | `packages/ui/src/index.ts` exports all components as named exports (no barrel files inside component subdirectories). |
| 5 | Each of the 6 apps imports from `@leapmoney/ui` successfully: verified by adding `import { Button } from "@leapmoney/ui"` to a stub page and confirming TypeScript resolves the import. |
| 6 | `pnpm turbo type-check` still passes across all apps after ui package is configured. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Configure `packages/ui/package.json` with correct name, exports, and peer dependencies | E2 | 0.5h | S0-04 |
| 2 | Initialise shadcn/ui in packages/ui; configure TypeScript + Tailwind + CSS variables mode | E2 | 1h | S0-05 |
| 3 | Install base shadcn/ui components (Button, Input, Label, Card, Badge, Dialog, Sheet, Table, Form, Select, Checkbox, RadioGroup, Textarea, Separator, Skeleton) | E2 | 1h | shadcn init |
| 4 | Install notification components: Toast, Sonner | E2 | 0.5h | shadcn components done |
| 5 | Write `packages/ui/src/index.ts` exporting all installed components as named exports | E2 | 0.5h | All components installed |
| 6 | Verify import resolution in each app: add test import of Button; run type-check; confirm 0 errors | E2 | 0.5h | index.ts complete |

S0-18 · Implement LeapMoney Design Tokens ●●●●●○○○ 5 pts · Owner: E2 — Full-Stack · Priority: Must Have

As a Full-Stack Engineer, I want to implement the LeapMoney design tokens from Phase 6 in the shared Tailwind and CSS variable configuration so that every component automatically uses brand-correct colours, typography, and spacing — designers see brand-accurate work from the first prototype.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | CSS variables defined in `packages/ui/src/globals.css` (or the base globals.css extended by each app) for: brand colours (`--leap-teal`, `--leap-navy`, `--leap-green`, `--leap-amber`, `--leap-red`), neutral scale, and semantic colours (background, foreground, muted, accent, destructive). |
| 2 | Tailwind config in `packages/config/tailwind/base.ts` extended with all LeapMoney tokens as Tailwind utility classes: `bg-leap-teal`, `text-leap-navy`, `border-leap-green`, etc. |
| 3 | Typography tokens: font family set to Inter (or system font stack with Inter as primary); font sizes follow Phase 6 scale (xs: 12px, sm: 14px, base: 16px, lg: 18px, xl: 20px, 2xl: 24px). |
| 4 | Spacing and border-radius tokens match Phase 6 design system: `rounded-leap` (8px for cards), `rounded-leap-sm` (4px for inputs), `rounded-leap-full` (9999px for badges). |
| 5 | shadcn/ui CSS variable mappings updated to use LeapMoney brand tokens — shadcn components automatically render in LeapMoney brand colours. |
| 6 | Design token reference page exists in `apps/web/src/app/design-tokens/page.tsx` (dev-only route) showing all colours, typography, and spacing — can be shown to designers for sign-off. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Define CSS custom properties for all LeapMoney brand colours (teal, navy, green, amber, red) and neutral scale in globals.css | E2 | 1h | S0-17 |
| 2 | Extend Tailwind config in packages/config with leap-* colour utilities and semantic colour mappings | E2 | 1h | CSS vars defined |
| 3 | Define typography tokens: font family (Inter), font size scale, line heights, font weights | E2 | 0.75h | S0-05 |
| 4 | Define spacing and border-radius tokens in Tailwind config | E2 | 0.5h | Tailwind extended |
| 5 | Update shadcn/ui CSS variable mappings to point to LeapMoney brand tokens | E2 | 0.75h | CSS vars and shadcn |
| 6 | Build design token reference page in apps/web; add all colour swatches, typography scale, spacing examples | E2 | 1h | All tokens defined |

S0-19 · Core Component Library Scaffold ●●●●●●●● 8 pts · Owner: E2 — Full-Stack · Priority: Must Have

As a Full-Stack Engineer, I want to have the LeapMoney-specific shared components built in `packages/ui` so that Sprint 1 feature stories can use pre-built, brand-correct components instead of building from scratch, accelerating every feature by 30–50%.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | `LeapScoreBadge` component: displays a LeapScore value (0–100) with band colour (Band 1: red, Band 2: orange, Band 3: yellow, Band 4: teal, Band 5: green); accepts `score: number` and `band: 1¦2¦3¦4¦5` props. |
| 2 | `LeapScoreMeter` component: horizontal progress bar showing score 0–100 with colour gradient matching the 5 bands; animated fill; accepts `score: number`. |
| 3 | `StatusBadge` component: pill-shaped badge for application/lead statuses; accepts `status: string` and maps to colour (e.g. "approved" → green, "rejected" → red, "pending" → amber, "in_review" → blue). |
| 4 | `DataCard` component: wrapper card with title, optional subtitle, optional icon, and content slot; used throughout all dashboards. |
| 5 | `EmptyState` component: full-width placeholder for empty data tables/lists; accepts `icon`, `title`, `description`, optional `action` button. |
| 6 | `PageHeader` component: standard page heading with title, optional breadcrumb, optional action button(s); used in all dashboard pages. |
| 7 | `LoadingSpinner` component: centred spinner for loading states; `FullPageLoader` variant for page-level loading. |
| 8 | `ConfirmDialog` component: wraps shadcn Dialog; accepts `title`, `description`, `confirmLabel`, `onConfirm`, `isDestructive` props; used for all delete/irreversible action confirmations. |
| 9 | All components exported from `packages/ui/src/index.ts`. |
| 10 | All components have TypeScript props interfaces defined with JSDoc comments. |
| 11 | All components are tested in the `apps/web` design token page — each component renders correctly with brand tokens applied. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Build `LeapScoreBadge` with 5-band colour mapping and props interface | E2 | 1h | S0-18 |
| 2 | Build `LeapScoreMeter` with animated gradient fill and band colour transitions | E2 | 1.5h | S0-18 |
| 3 | Build `StatusBadge` with status-to-colour mapping (approved, rejected, pending, in_review, disbursed) | E2 | 0.75h | S0-18 |
| 4 | Build `DataCard` wrapper component | E2 | 0.75h | S0-18 |
| 5 | Build `EmptyState` component | E2 | 0.5h | S0-18 |
| 6 | Build `PageHeader` with breadcrumb and action button slots | E2 | 0.75h | S0-18 |
| 7 | Build `LoadingSpinner` and `FullPageLoader` components | E2 | 0.5h | S0-18 |
| 8 | Build `ConfirmDialog` wrapping shadcn Dialog with destructive variant | E2 | 0.75h | S0-17 |
| 9 | Export all new components from packages/ui/src/index.ts | E2 | 0.25h | All components built |
| 10 | Add all components to design token reference page in apps/web; verify visual rendering with brand tokens | E2 | 0.5h | All components exported |

EPIC 7 · Authentication 4 Stories · 18 Story Points

Configure Supabase Auth, build the Borrower OTP login flow (mobile-first, phone-based), build the Staff (DSA/Lender/Admin) email/password login, and implement the auth middleware that protects all dashboard routes. All apps must have working authentication by the end of Sprint 0.

S0-20 · Supabase Auth Configuration ●●●○○○○○ 3 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a Tech Lead, I want to configure Supabase Auth with the correct providers, redirect URLs, and email/SMS templates so that all authentication flows have a correctly configured backend from day one, and OTP messages are sent from a recognisable LeapMoney sender.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | Supabase Auth configured in both staging and production projects: (a) Phone provider enabled for OTP (using Twilio or MSG91 as SMS provider), (b) Email provider enabled for staff authentication. |
| 2 | SMS OTP provider selected and configured: MSG91 preferred (Indian SMS provider, DLT registered) — API key in Supabase Auth settings and documented in 1Password. |
| 3 | OTP expiry set to 10 minutes (not the default 60 minutes) in Supabase Auth settings. |
| 4 | JWT expiry set to 1 hour (access token); refresh token expiry set to 30 days. |
| 5 | Redirect URLs allowlisted in Supabase Auth for each app: `https://app.leapmoney.net/auth/callback`, `https://dsa.leapmoney.net/auth/callback`, staging equivalents, and localhost variants for all apps. |
| 6 | Email templates customised (Supabase dashboard): LeapMoney branding on confirmation and reset emails. |
| 7 | Site URL set to `https://leapmoney.net` (production) and staging equivalent. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Enable Phone auth provider in Supabase Auth; configure MSG91 as SMS gateway; add API key | E1 | 1h | S0-10 |
| 2 | Enable Email provider in Supabase Auth for staff login | E1 | 0.25h | S0-10 |
| 3 | Set OTP expiry to 10 min and JWT expiry to 1h in Supabase Auth settings | E1 | 0.25h | S0-10 |
| 4 | Add all redirect URLs (production, staging, localhost for each app) to Supabase Auth allowed list | E1 | 0.5h | S0-15 |
| 5 | Customise email templates with LeapMoney branding (logo, colours, footer) | E1 | 0.75h | S0-10 |
| 6 | Document SMS provider credentials and Supabase Auth settings in 1Password | E1 | 0.25h | All auth settings |

S0-21 · Borrower OTP Login Flow ●●●●●●●● 8 pts · Owner: E2 — Full-Stack · Priority: Must Have

As a Borrower, I want to log in using my mobile phone number and a one-time password so that I can access my loan dashboard securely without remembering a password, using the same pattern I use with every other Indian financial app.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | Login page exists at `apps/borrower/src/app/(auth)/login/page.tsx` — renders a phone number input + "Send OTP" button; no password field. |
| 2 | Phone number input: accepts 10-digit Indian mobile numbers; validates format before enabling Send OTP button; displays "+91" prefix automatically. |
| 3 | On "Send OTP" click: calls Supabase `auth.signInWithOtp({ phone: "+91" + phoneNumber })`; shows loading state on button; on success shows OTP entry UI. |
| 4 | OTP entry UI: 6-box digit input (one digit per box) with auto-focus advancement; 30-second resend countdown timer. |
| 5 | On OTP verify: calls Supabase `auth.verifyOtp({ phone, token, type: "sms" })`; on success redirects to `/dashboard`. |
| 6 | Error states handled: invalid phone format (client-side validation), OTP expired (show "Code expired — resend" message), incorrect OTP (show "Incorrect code" with remaining attempts from Supabase error), rate limited (show "Too many attempts — try in 60 seconds"). |
| 7 | On successful auth: Supabase session stored in cookies (not localStorage); middleware reads cookie to protect dashboard routes. |
| 8 | Mobile-first: login page renders correctly on 375px viewport; OTP boxes are large enough for fat-finger tap targets (min 44×44px). |
| 9 | Accessibility: all inputs have ARIA labels; error messages announced via `aria-live`; keyboard navigation works end-to-end. |
| 10 | New user handling: if phone number is new (not in `users` table), a new user record and profile record are created via a Supabase database trigger on `auth.users` insert. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Create `(auth)/login/page.tsx` in apps/borrower with phone number input form using React Hook Form + Zod | E2 | 1.5h | S0-17, S0-20 |
| 2 | Wire "Send OTP" to Supabase `auth.signInWithOtp`; handle loading and error states | E2 | 1h | login page |
| 3 | Build 6-box OTP input component (auto-advance, backspace handling, paste support) | E2 | 1.5h | S0-17 |
| 4 | Wire OTP verify to Supabase `auth.verifyOtp`; handle all error cases with user-friendly messages | E2 | 1h | OTP component |
| 5 | Implement 30-second resend countdown timer; re-enable Send OTP after countdown | E2 | 0.5h | OTP verify working |
| 6 | Write Supabase DB trigger migration `019_new_user_trigger.sql`: on INSERT to auth.users → create users and profiles rows | E1 | 1h | S0-11 |
| 7 | Mobile-first layout audit: test on 375px; verify tap targets, font sizes, no horizontal overflow | E2 | 0.5h | Login flow complete |
| 8 | Accessibility audit: add ARIA labels and live regions; test with keyboard only | E2 | 0.5h | Login flow complete |

S0-22 · Staff Email / Password Authentication ●●●●●○○○ 5 pts · Owner: E2 — Full-Stack · Priority: Must Have

As a DSA / Lender / Admin, I want to log in using my email address and password so that I can access my dashboard securely without phone OTP, using a professional credential flow appropriate for business users who work on desktop.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | Login pages exist in `apps/dsa`, `apps/lender`, and `apps/admin` at `(auth)/login/page.tsx` — each renders email + password inputs and a "Sign In" button. |
| 2 | On submit: calls Supabase `auth.signInWithPassword({ email, password })`; shows loading state; on success redirects to `/(dashboard)`. |
| 3 | Error states handled: invalid credentials ("Incorrect email or password"), unverified email ("Please verify your email address"), too many attempts ("Account temporarily locked — try again in 15 minutes"). |
| 4 | "Forgot password" link navigates to `(auth)/forgot-password/page.tsx`; calls `auth.resetPasswordForEmail(email)`; shows confirmation message. |
| 5 | Password reset: user receives email from Supabase Auth; follows link to `(auth)/reset-password/page.tsx`; enters new password; calls `auth.updateUser({ password })`. Password requirements: min 8 characters, at least 1 number, at least 1 special character. |
| 6 | First-time user flow: DSAs and Lenders are created by Admin (not self-registered); Admin creates user via Supabase Auth admin API; user receives invite email with password reset link. |
| 7 | Session stored in cookies; middleware protects all dashboard routes; redirects to `/login` if session missing or expired. |
| 8 | Desktop-first layout: login pages optimised for 1280px+ viewport (centred card, branded sidebar with LeapMoney value proposition). |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Create `(auth)/login/page.tsx` in apps/dsa with email + password form (React Hook Form + Zod) | E2 | 1h | S0-17, S0-20 |
| 2 | Clone login page for apps/lender and apps/admin (same pattern, different branding colours) | E2 | 0.5h | DSA login done |
| 3 | Wire sign-in to Supabase `auth.signInWithPassword`; handle all error states | E2 | 0.75h | Login pages |
| 4 | Build forgot-password and reset-password pages in all 3 apps | E2 | 1.5h | S0-20 |
| 5 | Document first-user creation process: how Admin creates DSA/Lender accounts via Supabase dashboard | E1 | 0.5h | S0-24 |
| 6 | Desktop layout audit: verify all 3 login pages render correctly at 1280px; add branded sidebar | E2 | 0.75h | All login pages done |

S0-23 · Auth Middleware & Session Management ●●○○○○○○ 2 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a any engineer, I want to have Next.js middleware that reads the Supabase session from cookies and protects dashboard routes so that every dashboard route in all 6 apps is automatically protected — an unauthenticated user is always redirected to the login page, with no per-page auth check required.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | `src/middleware.ts` in each app is fully implemented (not a stub): reads Supabase session from cookies using `@supabase/ssr` package. |
| 2 | Matcher configured to protect `/(dashboard)/` route group: any request to a dashboard route without a valid session is redirected to `/login?redirectTo=<original-path>`. |
| 3 | After login, user is redirected to the `redirectTo` parameter value (or `/` as fallback). |
| 4 | Session refresh: middleware refreshes the Supabase session on every request using `supabase.auth.getSession()` — expired tokens are automatically refreshed via the refresh token cookie. |
| 5 | Auth routes (`/(auth)/login`, `/forgot-password`, `/reset-password`) are excluded from protection and accessible without a session. |
| 6 | Role guard in middleware: if the logged-in user's role does not match the app they are accessing (e.g. a borrower accessing `/dsa/dashboard`), they are redirected to their correct app. |
| 7 | Verified: accessing `/borrower/dashboard` without a session redirects to `/borrower/login?redirectTo=/borrower/dashboard`. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Install `@supabase/ssr` in all apps; configure server and client Supabase instances to use `@supabase/ssr` cookie helpers | E1 | 0.75h | S0-20, S0-07 |
| 2 | Implement full middleware.ts in all 6 apps: session read, redirect logic, redirectTo param handling | E1 | 1h | ssr package installed |
| 3 | Add role guard to middleware: read user role from session metadata; redirect if wrong app | E1 | 0.5h | S0-24 |
| 4 | Test: attempt to access dashboard in each app without session; confirm redirect to login with redirectTo | E1 | 0.5h | All middleware implemented |

EPIC 8 · RBAC — Role-Based Access Control 3 Stories · 13 Story Points

Define the role and permission model in Supabase, implement middleware-level route guards, and build the role-aware navigation shell that each app uses. Together with Epic 7, this completes the security foundation.

S0-24 · Roles & Permissions in Supabase ●●●●●○○○ 5 pts · Owner: E1 — Tech Lead · Priority: Must Have

As a Tech Lead, I want to define user roles and permissions in the Supabase database and auth metadata so that every part of the system — database RLS, API route handlers, and frontend middleware — reads from a single authoritative role definition, with no role logic duplicated across layers.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | User roles defined as a PostgreSQL enum type: `CREATE TYPE user_role AS ENUM ('borrower', 'dsa', 'dsa_manager', 'lender', 'lender_admin', 'admin', 'super_admin')`. |
| 2 | `role` column added to the `users` table using the `user_role` enum type; default value `'borrower'`. |
| 3 | Role stored in Supabase Auth JWT custom claims via a `custom_access_token_hook` database function: on every token refresh, the user's role is read from the `users` table and injected into `app_metadata.role` in the JWT. |
| 4 | `custom_access_token_hook` function created and enabled in Supabase Auth hooks settings. |
| 5 | Permissions matrix documented in code (`packages/types/src/permissions.ts`): a TypeScript object mapping each role to the set of actions they can perform (e.g. `borrower: ["leads:read:own", "applications:read:own", "documents:write:own"]`). |
| 6 | RLS policies updated (migration `020_rls_role_claims.sql`) to use `(auth.jwt()->>'role')` from JWT claims rather than a separate join — faster and no function call overhead. |
| 7 | Verified: Supabase SQL editor shows `auth.jwt()->>'role'` returns the correct role for a test user of each type. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Write migration `019_roles.sql`: create user_role enum; add role column to users table; backfill existing rows to 'borrower' | E1 | 0.5h | S0-11 |
| 2 | Write `custom_access_token_hook` PL/pgSQL function in migration `020_jwt_claims.sql`: reads role from users table, sets app_metadata.role in JWT | E1 | 1.5h | role column exists |
| 3 | Enable the custom_access_token_hook in Supabase Auth dashboard settings | E1 | 0.25h | hook function deployed |
| 4 | Write `packages/types/src/permissions.ts` with full permissions matrix for all 7 roles | E1 | 1h | roles defined |
| 5 | Update RLS migration `021_rls_role_claims.sql`: replace any `JOIN users` role lookups with `auth.jwt()->>'role'` pattern | E1 | 1h | S0-12, JWT claims |
| 6 | Test JWT claims: create test users of each role; verify auth.jwt()->>'role' returns correct value in SQL editor | E1 | 0.75h | hook enabled |

S0-25 · RBAC Middleware Guards & Route Protection ●●●●●○○○ 5 pts · Owner: E1 + E2 · Priority: Must Have

As a Tech Lead, I want to implement RBAC middleware guards in all apps that verify the user's role matches the app's allowed roles so that a borrower who somehow navigates to the DSA portal is immediately redirected to their own app, and a DSA cannot access the Admin portal even if they have a valid session.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | Each app has a constant defining its allowed roles: `apps/borrower`: `['borrower']`, `apps/dsa`: `['dsa', 'dsa_manager']`, `apps/lender`: `['lender', 'lender_admin']`, `apps/admin`: `['admin', 'super_admin']`. |
| 2 | Middleware in each app reads `session.user.app_metadata.role` from the Supabase JWT claims (set by S0-24 hook); if the role is not in the app's allowed list, the user is redirected to a `/unauthorised` page. |
| 3 | `/unauthorised` page exists in all apps: displays a clear message explaining the user does not have access, with a link to the correct app for their role. |
| 4 | API route handlers in each app verify role on every request via a `requireRole(allowedRoles)` helper function in `src/lib/auth/require-role.ts`; returns 403 if role check fails. |
| 5 | `requireRole` function reads the session from the request using `@supabase/ssr`; returns typed session or throws an `UnauthorisedError`. |
| 6 | Verified: log in as a borrower; attempt to access `/dsa/dashboard`; confirm redirect to `/unauthorised`. |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Define `ALLOWED_ROLES` constant in each app's `src/lib/auth/config.ts` | E1 | 0.5h | S0-24 |
| 2 | Update middleware in each app to read JWT role and compare against ALLOWED_ROLES; redirect to /unauthorised if mismatch | E1 | 1h | S0-23, S0-24 |
| 3 | Create `/unauthorised/page.tsx` in all apps with clear message and role-appropriate redirect link | E2 | 1h | S0-17 |
| 4 | Write `requireRole(allowedRoles)` helper in `src/lib/auth/require-role.ts` for use in API route handlers | E1 | 0.75h | S0-23 |
| 5 | Add `requireRole` call to at least one API route per app as a proof-of-concept | E1 | 0.5h | requireRole written |
| 6 | Test: log in as borrower; access DSA dashboard; confirm /unauthorised redirect | E1 | 0.25h | All RBAC in place |

S0-26 · Role-Based Navigation Shell ●●●○○○○○ 3 pts · Owner: E2 — Full-Stack · Priority: Must Have

As a any logged-in user, I want to see a navigation sidebar and header that match my role and shows only the features I have access to so that the dashboard feels purpose-built for my role — I don't see confusing menu items I cannot access, and navigation is immediately intuitive.

| # | Acceptance Criterion — Pass when: |
| --- | --- |
| 1 | `Sidebar` component in each app's `src/components/layout/Sidebar.tsx` renders navigation items specific to that app's role. |
| 2 | Borrower app sidebar items: "My Dashboard", "Apply for Loan", "My Applications", "My LeapScore", "Documents", "Help". |
| 3 | DSA app sidebar items: "Dashboard", "Leads", "Applications", "My Performance", "Commissions", "Profile". |
| 4 | Lender app sidebar items: "Dashboard", "Pending Applications", "Approved", "Disbursed", "Products". |
| 5 | Admin app sidebar items: "Dashboard", "Users", "Leads (All)", "Applications (All)", "Feature Flags", "Audit Log", "System Health". |
| 6 | `Header` component in each app's `src/components/layout/Header.tsx` shows: app-specific logo/title, logged-in user's name, role badge, and "Sign Out" button. |
| 7 | Sign out: calls `supabase.auth.signOut()`; clears session cookie; redirects to `/login`. |
| 8 | Active nav item highlighted with brand colour; nav items are links (not buttons) for correct browser history behaviour. |
| 9 | Sidebar collapses to icon-only mode on mobile (below 768px viewport). |

| # | Task | Owner | Est. | Depends On |
| --- | --- | --- | --- | --- |
| 1 | Build `Sidebar` component for apps/borrower with correct nav items; active state highlighting | E2 | 1h | S0-18 |
| 2 | Build `Sidebar` components for apps/dsa, apps/lender, apps/admin (each with correct nav items) | E2 | 1.5h | Borrower sidebar done |
| 3 | Build shared `Header` component for all apps: user name, role badge, sign-out button | E2 | 0.75h | S0-18 |
| 4 | Wire sign-out: `supabase.auth.signOut()` + clear cookie + redirect to /login | E2 | 0.5h | Header built, S0-23 |
| 5 | Add responsive collapse: sidebar icon-only mode below 768px | E2 | 0.75h | All sidebars built |
| 6 | Wire Sidebar and Header into each app's `(dashboard)/layout.tsx`; smoke test all 4 apps | E2 | 0.5h | Components built |

# Sprint 0 Dependency Map

The table below shows which stories are blocked by other stories within Sprint 0. Stories not listed have no intra-sprint dependencies and can start immediately.

| Story | Title | Blocked By | Can Start |
| --- | --- | --- | --- |
| S0-01 | GitHub Org & Repository | None | Day 1 — First story of Sprint 0 |
| S0-02 | Branch Protection | S0-01 | After S0-01 is merged (~Day 1 afternoon) |
| S0-03 | PR & Issue Templates | S0-01 | After S0-01 is merged |
| S0-04 | Turborepo Monorepo Init | S0-01 | Day 2 (after .gitignore and README committed) |
| S0-05 | Shared packages/config | S0-04 | After S0-04 is merged |
| S0-06 | Remote Caching | S0-04 | After S0-04 (requires Vercel account — start Vercel setup in parallel) |
| S0-07 | Scaffold 6 Next.js Apps | S0-04 | After S0-04 (E1 and E2 can work in parallel — E1 scaffolds web+borrower, E2 scaffolds dsa+lender+admin+referral) |
| S0-08 | Env Variable Management | S0-07, S0-10 (for Supabase URLs) | After S0-07 scaffold and S0-10 project provisioning |
| S0-09 | Next.js App Config | S0-07 | After S0-07 |
| S0-10 | Provision Supabase Projects | None | Day 1 (can be done in parallel with S0-01) |
| S0-11 | Database Schema Migrations | S0-10 | After S0-10 (Supabase CLI + project ref needed) |
| S0-12 | RLS Policies | S0-11 | After all migration files in S0-11 are written and tested |
| S0-13 | Storage Buckets | S0-10, S0-12 (for storage RLS) | After S0-10; storage RLS after S0-12 |
| S0-14 | CI Pipeline | S0-04, S0-05 | After monorepo and config are in place so lint/type-check can run |
| S0-15 | Vercel Deployment | S0-07, S0-14 (CI must pass before deploy) | After apps are scaffolded and CI is green |
| S0-16 | Security Scanning | S0-01 (GitHub Actions) | After S0-01; can run in parallel with S0-14 |
| S0-17 | packages/ui shadcn/ui | S0-04, S0-05 | After monorepo and config are in place |
| S0-18 | Design Tokens | S0-17 | After S0-17 |
| S0-19 | Core Components | S0-17, S0-18 | After S0-18 |
| S0-20 | Supabase Auth Config | S0-10 | After Supabase projects are provisioned |
| S0-21 | Borrower OTP Login | S0-07, S0-17, S0-20 | After app scaffold, packages/ui base, and auth config |
| S0-22 | Staff Email Auth | S0-07, S0-17, S0-20 | Same as S0-21 |
| S0-23 | Auth Middleware | S0-21, S0-22 (to test with real auth) | Can stub before; fully wired after S0-21/22 |
| S0-24 | Roles in Supabase | S0-11 (users table) | After S0-11 has users table with role column |
| S0-25 | RBAC Middleware Guards | S0-23, S0-24 | After auth middleware and roles are in place |
| S0-26 | Role-Based Nav Shell | S0-17, S0-18, S0-25 | After design tokens and RBAC guards |

## External Dependencies (Pre-Sprint 0 Actions Required)

| Dependency | Required For | Action Required | Who | Deadline |
| --- | --- | --- | --- | --- |
| MSG91 or Twilio SMS account | S0-20 (Supabase Auth OTP) | Create MSG91 account; complete DLT registration for OTP SMS template; obtain API key | Founder / Tech Lead | Before Sprint 0 Day 6 |
| Sentry account | S0-09 (error tracking) | Create Sentry organisation; create 5 projects (one per app); obtain DSNs | Tech Lead | Before Sprint 0 Day 1 |
| 1Password Teams account | S0-10 (secrets vault) | Create 1Password Teams account; add all team members; create "LeapMoney Infrastructure" vault | Founder | Before Sprint 0 Day 1 |
| Vercel Pro/Team account | S0-15 (deployment) | Create Vercel account; upgrade to Pro (required for team features and higher build concurrency) | Founder | Before Sprint 0 Day 10 |
| GitHub Team plan | S0-02 (branch protection) | Upgrade org to Team plan (branch protection requires paid plan) | Founder | Before Sprint 0 Day 1 |

# Appendix A — Story Point Reference Scale

This table defines the story point scale for the LeapMoney engineering team. All engineers use the same scale. 1 point = approximately 2 hours of focused engineering work on familiar code.

| Points | Size | Typical Work | Sprint 0 Examples |
| --- | --- | --- | --- |
| 1 | Micro | A single, trivial change — one config value, one line of code, one setting toggle | — |
| 2 | XS | A small, clearly defined change in a known area with no unknowns | S0-03: PR Templates |
| 3 | S | A contained task with a clear approach — a few files, a well-understood pattern | S0-02, S0-06, S0-08, S0-09, S0-10, S0-20, S0-23 |
| 5 | M | Moderate scope — multiple files, some decisions to make, 1–2 unknowns | S0-01, S0-05, S0-13, S0-15, S0-17, S0-18, S0-24, S0-25, S0-26 |
| 8 | L | Significant scope — a full feature or system component, several files, clear pattern exists | S0-04, S0-07, S0-12, S0-14, S0-19, S0-21, S0-22 |
| 13 | XL | Complex — high scope, multiple unknowns, architectural decisions, significant testing | S0-11: Complete DB Schema (8 migration files) |
| 21 | Epic | Too large — must be split before entering a sprint | Any story estimated at 21+ must be decomposed into 2+ stories |

Estimation Rule If two engineers disagree on a point estimate by more than one size band (e.g. one says 3, the other says 8), do not average — discuss until you understand the difference. The engineer with the higher estimate has likely identified complexity the other missed.

# Appendix B — Sprint 0 Risk Register

| Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| MSG91 DLT registration takes >5 days — OTP SMS cannot be sent in Sprint 0 | High (DLT process is slow in India) | High — S0-21 Borrower OTP flow cannot be fully tested | Start DLT registration on Day 1 of Sprint 0 (not Day 6). Use Twilio as fallback for testing (international SMS, no DLT required). Document which stories are blocked by this external dependency. | Founder + E1 |
| CIBIL sandbox access delayed — bureau integration blocked in Sprint 1 | High (bureau onboarding takes 2–4 weeks) | Medium — Sprint 2 stories S2-xx blocked; workaround is mock bureau data | Initiate CIBIL and Experian sandbox application on Sprint 0 Day 1. Use mock bureau response in Sprint 1. Escalate daily if no response by Sprint 0 Day 5. | Founder |
| S0-11 (DB schema) takes longer than estimated (13 pts on one engineer) | Medium | High — S0-12, S0-13, S0-21, S0-24 all depend on S0-11 | Break S0-11 into daily targets: 3 migration files per day over 3 days. If behind by Day 8, E2 picks up non-dependent work (design system) to avoid idle time. De-scope notification tables (S0-11 migration 009) to Sprint 1 if needed. | E1 |
| RLS policies have subtle bugs that allow cross-tenant data access | Low | Critical — financial data leak in production | S0-12 includes mandatory RLS testing with role-switching (AC item 11). No story that reads data is marked Done until RLS is verified. Consider a dedicated RLS review session with Tech Lead before Sprint 0 sign-off. | E1 |
| E2 unavailable for a portion of Sprint 0 | Low | Medium — design system and borrower auth delayed | E2 stories (Epics 6–7) are lowest-priority in Sprint 0 since they can be delivered into early Sprint 1 without unblocking Sprint 1 data work. Reprioritise Sprint 1 plan if E2 is delayed more than 3 days. | E1 |

# Appendix C — Sprint 0 Definition of Done (Infrastructure Focus)

Sprint 0 has a modified DoD vs Sprint 1+ because some items (unit tests for infrastructure scaffolding) are not applicable. The following DoD applies to ALL Sprint 0 stories:

| # | Sprint 0 DoD Item | Applies To |
| --- | --- | --- |
| 1 | Code is merged to `develop` branch via an approved, squash-merged PR | All stories |
| 2 | All CI checks pass: lint, type-check (and unit tests where applicable) | All stories |
| 3 | No TypeScript errors in any changed file (`pnpm turbo type-check` clean) | All stories |
| 4 | No `console.log`, `// @ts-ignore`, or `any` type in committed code | All stories |
| 5 | The feature/configuration is manually verified on the Vercel staging URL (or local for pre-deployment stories) | All stories from S0-09 onwards |
| 6 | RLS policies tested with role-switching for any story that touches database access control | S0-12, S0-24, S0-25 |
| 7 | Secrets confirmed absent from code: Gitleaks scan passes on the PR | All stories |
| 8 | The story's acceptance criteria are all checked off in the PR description | All stories |
| 9 | Notion story status updated to Done; PR linked to story | All stories |
| 10 | Tech Lead has verified the implementation matches the Phase 12 Development Execution Blueprint standards | All stories |

# Appendix D — Sprint 0 Sign-Off Checklist

Tech Lead and Founder use this checklist at the Sprint 0 Review to confirm Sprint 0 is complete and Sprint 1 can begin.

| Domain | Sign-Off Item | Verified By |
| --- | --- | --- |
| GitHub | All 26 stories merged to `develop`; branch protection active on main and develop; Dependabot enabled | Tech Lead |
| Monorepo | `pnpm install` succeeds from root; `pnpm turbo build` runs without errors across all 6 apps | Tech Lead |
| CI/CD | CI pipeline runs and passes on a dummy PR; Vercel preview deploys successfully; Gitleaks and CodeQL active | Tech Lead |
| Supabase | `supabase db reset` applies all migrations cleanly; all tables exist; `supabase gen types` output is committed | Tech Lead |
| RLS | Cross-tenant data isolation verified with role-switching tests for all critical tables | Tech Lead |
| Design System | All 6 apps render with LeapMoney brand tokens; core component library is accessible in apps/web design page | E2 |
| Authentication | Borrower OTP flow works end-to-end on staging: enter phone → receive OTP → log in → see dashboard | E1 + E2 |
| Authentication | DSA and Admin email/password login works end-to-end on staging | E2 |
| RBAC | Borrower accessing /dsa is redirected to /unauthorised; JWT role claims verified | E1 |
| Security | Gitleaks CI job blocks a PR with a test secret; CodeQL shows 0 high-severity findings | Tech Lead |
| Documentation | README onboarding: new engineer can clone repo and run `supabase start` + `pnpm dev` in under 30 minutes | Tech Lead |
| Sprint Review | Founder has seen live demo of: auth flow, dashboard navigation, design system component page | Founder |